## Sheet1
Number | Role | Type | Content | Reference
1.0 | MD | Heading | Pre-Action Safety Information
1.1 | MD | Warning | Review applicable safety information, from documents located in Mission Specific Release Folder. Failure to consider guidelines may result in personal injury or death. | http://somewhere on the net
1.2 | MD | Action | Make required safety announcement on VL-AZERO
2.0 | SYS,CC | Heading | Establish Com Link
2.1.0 | CC | Heading | Prepare Ground Support Equipment
2.1.1 | CC | Action | Powerup GSE Rack if necessary
2.1.2 | CC | Record | Verify UPS battery is fully charged, record charge state
2.1.3 | CC | Caution | If UPS battery charge is below 20%, consider replacement or postpone until full charge state (90%+) is reached. A low charge state may cause brown out during operations which can damage GSE equipment.
2.2.0 | SYS | Verify | Verify that OBC is fully booted and in state "idle"
2.2.1 | SYS | Record | Record OBC temperature as indiciated in telemetry channel "avi_obc_temp_core_calibrated".
2.2.2 | SYS | Decision | If recorded temperature exceeds 75 deg C, open instance of procedure 5.23 - Audacy Zero OBC cooling adjustment | http://direct link to open new procedure instance (latest rev)
2.3 | MD | Verify | Verify correct command list is loaded in the Command Qwidget for current OBC image revision as indiciated in "obc_image_version"
2.4 | MD, CC | Action | Issue null command and confirm response
3.0 | MD |  | Close Procedure
3.1 | MD | Action | Update the shift log with procedure close status / notes
3.2 | MD | Action | Close the procedure in Quantum (complete this step)